OBJECT-ORIENTED SOFTWARE ENGINEERING
UNIT 02 : PROJECT MANAGEMENT, PLANNING AND RISK ANALYSIS
© 2019, PRAMOD PARAJULI

---
Disclaimer
These slides are part of teaching materials for Object Oriented Software Engineering (OOSE). These slides do not cover all aspect of learning OOSE, nor are these be taken as primary source of information. As the core textbooks and reference books for learning the subject has already been specified and provided to the students, students are encouraged to learn from the original sources.
Contents in these slides are copyrighted to the instructor and authors of original texts where applicable.

---
COCOMO
UNIT 02: PROJECT MANAGEMENT
COCOMO

---
Software Cost Estimation Methods
Software Cost Estimation Methods
- Cost estimation: prediction of both the person-effort and elapsed time of a project
- Methods:
  - Algorithmic
  - Expert judgment
  - Estimation by analogy
  - Parkinsonian
- Best approach is a combination of methods
  - compare and iterate estimates, reconcile differences
- COCOMO - the “COnstructive COst MOdel”
  - COCOMO II is the update to Dr. Barry Boehm’s COCOMO 1981
- COCOMO is the most widely used, thoroughly documented and calibrated cost model
Price-to-win
Top-down
Bottom-up

---
INTRODUCTION
INTRODUCTION
- proposed by Barrey W. Boehm in 1981.
- Empirical software estimation model in the world.
- Predicts the effort and duration of a project based on :
- inputs relating to the size of the resulting systems and
- number of "cost drives" that affect productivity.

---
The Development Mode
The Development Mode
1. Organic mode :
  1. Relatively simple ,
  2. small projects with a small team are handled .
  3. good application experience to less rigid requirements.
2. Semidetached mode:
  1. For intermediate software projects(little complex compared to organic mode projects in terms of size).
  2. have a mix of rigid and less than rigid requirements.
3.Embedded mode:
  1. Project to be developed within a tight set of hardware and software operational constraints.
  2. Example of complex project: Air traffic control system

---
The coefficients of Aa, bb, cc, dd for the three modes are:
	Aa	bb	cc	dd
Organic	2.4	1.05	2.5	0.38
Semi-Detached	3.0	1.12	2.5	0.35
Embedded	3.6	1.20	2.5	0.32

---
COCOMO: Some Assumptions
COCOMO: Some Assumptions
- Primary cost driver is the number of Delivered Source Instructions (DSI) / Delivered Line Of Code developed by the project
- COCOMO estimates assume that the project will enjoy good management by both the developer and the customer
- Assumes the requirements specification is not substantially changed after the plans and requirements phase.

---
Forms of COCOMO Models
Forms of COCOMO Models
COCOMO is defined in terms of three different models:
  - Basic model,
  - Intermediate model, and
  - Detailed model.
Basic Model:
  1. a function of program size expressed in terms of lines of Code (LOC).
  2. good for quick, early, rough order of magnitude estimates of software costs .

---
1.Basic COCOMO
 1.Basic COCOMO
- a function of program size expressed in terms of lines of Code (LOC).
- good for quick, early, rough order of magnitude estimates of software costs
- It does not account for differences in
  - hardware constraints,
  - personnel quality and experience,
    - use of modern tools and techniques, and
    - other project attributes

---
1.Basic COCOMO
 1.Basic COCOMO
The basic COCOMO model takes the following form:
E=ab (KLOC)bb persons-months
D=cb (E)db months
where,
E	- Stands for the effort applied in terms of person months
D	- Development time in chronological months
KLOC	- Kilo lines of code of the project.
From E & D we can compute the no. of people required to accomplish the project as
N=E/D

---
1.Basic COCOMO
 1.Basic COCOMO
Merits
good for quick, early, rough order of magnitude estimates of software project.
Limitations
- Limited Accuracy: does not consider certain factors (hardware constraints, personal quality and experiences, modern techniques and tools ) for cost estimation of software.
- The estimates within a factor of 1.3 only 29% of the time and within the factor of 2 only 60% of time.

---
1.Basic COCOMO
 1.Basic COCOMO
Example: Consider your team is developing a software project using semi-detached mode with 30,000 lines of code . We will obtain estimation for this project as follows:
(1)Effort estimation
(2) Duration estimation
(3)Person estimation

---
1.Basic COCOMO
 1.Basic COCOMO
Example: Consider your team is developing a software project using semi-detached mode with 30,000 lines of code . We will obtain estimation for this project as follows:
(1)Effort estimation
E= a (KLOC)b	person-months
E=3.0(30)1.12	= 135.36 (136)
(2) Duration estimation
D=c (E)d	months
  D=2.5 (136) 0.35	= 13.95 (14)
(3)Person estimation
N=E/D	persons
N =136/14 = 9.7 (10)

---
2. Intermediate COCOMO
2. Intermediate COCOMO
Computes effort as a function of program size and a lot of cost drivers that includes subjective assessment of
  - product attributes,
  - hardware attributes,
  - personal attributes and
  - project attributes

---
	Cost Driver	COCOMO_II Post Architecture	COCOMO_II Early Design	REVIC	COCOMO_87	COCOMO_81 & COCOMO_85
Personnel Factors
ACAP	Analyst Capability	Yes		Yes	Yes	Yes
APEX AEXP	Applications Experience	Yes		Yes	Yes	Yes
PCAP	Programmer Capability	Yes		Yes	Yes	Yes
LEXP	Programming Language Experience			Yes	Yes	Yes
VEXP	Virtual Machine Experience			Yes	Yes	Yes
PERS	Personnel Capability		Yes
PREX	Personnel Experience		Yes
PCON	Personnel Continuity	Yes
PLEX PEXP	Platform Experience	Yes
LTEX	Language and Tool Experience	Yes
Product Factors
RELY	Required Software Reliability	Yes		Yes	Yes	Yes
DATA	Database Size	Yes		Yes	Yes	Yes
CPLX	Software Product Complexity	Yes		Yes	Yes	Yes
RUSE	Required Reusability	Yes	Yes	Yes	Yes
DOCU	Documentation Match to Life-Cycle Needs	Yes
RCPX	Product Reliability and Complexity		Yes

---
	Cost Driver	COCOMO_II Post Architecture	COCOMO_II Early Design	REVIC	COCOMO_87	COCOMO_81 & COCOMO_85
Platform Factors
TIME	Execution Time Constraint	Yes		Yes	Yes	Yes
STOR	Main Storage Constraint	Yes		Yes	Yes	Yes
TURN	Computer Turnaround Time			Yes	Yes	Yes
VIRT	Virtual Machine Volatility			Yes		Yes
VMVH	Virtual Machine Volatility: Host				Yes
VMVT	Virtual Machine Volatility: Target				Yes
PVOL	Platform Volatility	Yes
PDIF	Platform Difficulty		Yes
PLAT	Platform			Yes
Project Factors
TOOL	Use of Software Tools	Yes		Yes	Yes	Yes
MODP	Modern Programming Practices			Yes	Yes	Yes
SCED	Required Development Schedule	Yes	Yes	Yes	Yes	Yes
SECU	Classified Security Application			Yes	Yes
SITE	Multisite Development	Yes
FCIL	Facilities		Yes
RVOL	Requirements Volatility			Yes

---
2. Intermediate COCOMO
2. Intermediate COCOMO
- Based on the rating effort multipliers is determined. The product of all effort Multipliers result in “effort adjustment factor” (EAF). The intermediate COCOMO takes the form.
- E = ai (KLOC)bi × EAF	where
  E	- Effort applied in terms of person-months
KLOC	- Kilo lines of code for the project
 EAF	- It is the effort adjustment factor
The duration and person estimate is same as in basic COCOMO model i.e;
D = cb (E)db months i.e; use values of cb and db coefficients.
N=E/D persons

---
2. Intermediate COCOMO
The values of ai and bi for various class of software projects are:
Software Projects	Ai	Bi
Organic	3.2	1.05
Semi-detached	3.0	1.12
Embedded	2.8	1.20

---
2. Intermediate COCOMO
2. Intermediate COCOMO
Merits:
- This model can be applied to almost entire software product for easy and rough cost estimation during early stage.
- It can also be applied at the software product component level for obtaining more accurate cost estimation.
Limitations:
- The effort multipliers are not dependent on phases.
- A product with many components is difficult to estimate.

---
2. Intermediate COCOMO
2. Intermediate COCOMO
Example: Consider your team is developing a project having 30,000 lines of code which in an embedded software with critical area hence reliability is high .
The estimation can be
E = a (KLOC)bi × EAF
As reliability is high
EAF=1.15 (product attribute)
ai =
bi =
E =
 D = cb (E)db
     =
N = E/D

---
2. Intermediate COCOMO
2. Intermediate COCOMO
Example: Consider your team is developing a project having 30,000 lines of code which in an embedded software with critical area hence reliability is high .
The estimation can be
E = a (KLOC)bi × EAF
As reliability is high
EAF=1.15 (product attribute)
ai =2.8
bi =1.20 for embedded software
E = 2.8 (30)1.20 × 1.15
   = 191 person month
 D = cb (E)db
     = 2.5(191) 0.32
   = 13 months approximately
N = E/D
    = 191/13
N = 15 persons approx.

---
3. Detailed COCOMO Model
3. Detailed COCOMO Model
- Detailed COCOMO incorporates all characteristics of the intermediate version with an assessment of the cost driver’s impact on each phase of the development process.
- This helps in determining the man power allocation for each phase of the project.

---
3. Detailed COCOMO Model
3. Detailed COCOMO Model
Phase-Sensitive Effort Multipliers:
  - Some phases( Design, programming, integration/test)are more affected than others by factors defined by the cost drivers.
- Three –Level Product Hierarchy:
  - Modules,
  - Sub-System, and
  - System Levels
- The rating of the cost drivers are done at appropriate level. i.e. the level at which it is most suspicious to variation.

---
3. Detailed COCOMO Model
3. Detailed COCOMO Model
Phases
  - Plans and requirements
  - System Design
  - Detailed Design
  - Module code and test
  - Integrate and test
Cost of each subsystem is estimated separately. This reduces the margin of error.

---
3. Detailed COCOMO Model
3. Detailed COCOMO Model
- Multiply all 15 Cost Drivers to get Effort Adjustment Factor(EAF)
- E(Effort) = ab(KLOC)bb × EAF(in Person-Month)
- D(Development Time) = cb(E)db (in month)
- Ep (Total Effort) = µp × E (in Person-Month)
- Dp (Total Development Time) = τp × D (in month)

---
3. Detailed COCOMO Model
3. Detailed COCOMO Model
Consider you are developing a full screen editor as a project. The major components identified and their sizes are
  1. Screen Edit – 4K
  2. Command Lang Interpreter – 2K
  3. File Input and Output – 1K
  4. Cursor movement – 2K
  5. Screen Movement – 3K.
Assume the Required software reliability is high, product complexity is high, analyst capability is high & programming language experience is low. Use COCOMO model to estimate cost and time for different phases.

---
3. Detailed COCOMO Model
3. Detailed COCOMO Model
Size of modules : 4 + 2 + 1 + 2 + 3 = 13 KLOC [Organic]
EAF = 1.15 * 1.15 * 0.86 * 1.07 = 1.2169
Cost Drivers	Very Low	Low	Nominal	High	Very High	Extra High
RELY	0.75	0.88	1.00	1.15	1.40	--
CPLX	0.70	0.85	1.00	1.15	1.30	1.65
ACAP	1.46	1.19	1.00	0.86	0.71
LEXP	1.14	1.07	1.00	0.95	--	--

---
3. Detailed COCOMO Model
3. Detailed COCOMO Model
Initial Effort (E) = ab(KLOC)bb × EAF = 3.2 (12)1.05 × 1.2169
= 52.9 person-months
Initial Development Time (D) = cb(E)db =2.5*(52.9)0.38 = 11.29 months
Phase value of µp and τp
	Plan & Req	System Design	Detail Design	Module code & test	Integration & Test
Organic Small µp	0.06	0.16	0.26	0.42	0.16
Organic Small τp	0.10	0.19	0.24	0.39	0.18

---
3. Detailed COCOMO Model
3. Detailed COCOMO Model
Phase wise effort & development time distribution
	E	D	Ep (in person-months)	Dp (in months)
Plan & Requirement	52.9	11.29	0.06*52.9 = 3.17	0.10*11.29=1.12
System Design
Detail Design
Module code & test
Integration & test
Reference: COCOMO-I, Classroom Presentation, Jagat Man Mulguthi, NCIT, Spring 2018

---
COCOMO-II
UNIT 02: PROJECT MANAGEMENT
COCOMO-II
Reference: Cost Estimation with COCOMO II, Barry Boehm, University of Southern California

---
COCOMO Black Box Model
COCOMO Black Box Model
product size estimate
development, maintenance
cost and schedule estimates
product, process,
platform, and personnel
attributes
COCOMO II
reuse, maintenance,
and increment parameters
cost, schedule distribution by
phase, activity, increment
organizational
project data
recalibration to
 organizational data

---
COCOMO Effort Formulation
COCOMO Effort Formulation
        # of cost drivers
Effort (person-months) = A (Size)E Π Σmi
i=1
Where:
  - A is a constant derived from historical project data
    (currently A = 2.94 in COCOMOII.2000)
  - Size is in KSLOC (thousand source lines of code),
    or converted from function points or object points
  - Σ is an exponent for the diseconomy of scale dependent on five additive scale drivers according to
    b = .91 + .01×ΣSFi,
    where SFi is a weighting factor for ith scale driver
  - ΣMi is the effort multiplier for the ith cost driver. The geometric product results in an overall effort adjustment factor to the nominal effort.
Automated translation effects are not included

---
Diseconomy of Scale
Diseconomy of Scale
Nonlinear relationship when exponent > 1

---
COCOMO Schedule Formulation
COCOMO Schedule Formulation
Where:
  - Schedule is the calendar time in months from the requirements baseline to acceptance
  - C is a constant derived from historical project data
    (currently C = 3.67 in COCOMOII.2000)
  - Effort is the estimated person-months excluding the SCED effort multiplier
  - E is the exponent in the effort equation
  - SCED% is the compression / expansion percentage in the SCED cost driver
- This is the COCOMOII.2000 calibration
- Formula can vary to reflect process models for reusable and COTS software, and the effects of application composition capabilities.
Schedule (months) = C (Effort)(.33+0.2(E-1.01)) x SCED% / 100

---
RUP/ICSM Phase Distributions
RUP/ICSM Phase Distributions
Phase
Effort %
Schedule %
Inception
6
12.5
Elaboration
24
37.5
76
Construction
62.5
Transition
12
12.5
COCOMO Total
100
100
Project Total
118
125

---
COCOMO II  Output Ranges
COCOMO II Output Ranges
- COCOMO II provides one standard deviation optimistic and pessimistic estimates.
- Reflect sources of input uncertainties per funnel chart.
- Apply to effort or schedule for all of the stage models.
- Represent 80% confidence limits: below optimistic or pessimistic estimates 10% of the time.

---
Reused and Modified Software
Reused and Modified Software
- Effort for adapted software (reused or modified) is not the same as for new software.
- Approach: convert adapted software into equivalent size of new software.

---
Nonlinear Reuse Effects
Nonlinear Reuse Effects
- The reuse cost function does not go through the origin due to a cost of about 5% for assessing, selecting, and assimilating the reusable component.
- Small modifications generate disproportionately large costs primarily due the cost of understanding the software to be modified, and the relative cost of interface checking.

---
Nonlinear Reuse Effects
Nonlinear Reuse Effects

---
COCOMO Reuse Model
COCOMO Reuse Model
A nonlinear estimation model to convert adapted (reused or modified) software into equivalent size of new software:

---
COCOMO Reuse Model cont’d
COCOMO Reuse Model cont’d
- ASLOC - Adapted Source Lines of Code
- ESLOC - Equivalent Source Lines of Code
- AAF - Adaptation Adjustment Factor
- DM - Percent Design Modified. The percentage of the adapted software's design which is modified in order to adapt it to the new objectives and environment.
- CM - Percent Code Modified. The percentage of the adapted software's code which is modified in order to adapt it to the new objectives and environment.
- IM - Percent of Integration Required for Modified Software. The percentage of effort required to integrate the adapted software into an overall product and to test the resulting product as compared to the normal amount of integration and test effort for software of comparable size.
- AA - Assessment and Assimilation effort needed to determine whether a fully-reused software module is appropriate to the application, and to integrate its description into the overall product description. See table.
- SU - Software Understanding. Effort increment as a percentage. Only used when code is modified (zero when DM=0 and CM=0). See table.
- UNFM - Unfamiliarity. The programmer's relative unfamiliarity with the software which is applied multiplicatively to the software understanding effort increment (0-1).

---
Assessment and Assimilation Increment (AA)
Assessment and Assimilation Increment (AA)

---
Software Understanding Increment (SU)
Software Understanding Increment (SU)
- Take the subjective average of the three categories.
- Do not use SU if the component is being used unmodified (DM=0 and CM =0).

---
Programmer Unfamiliarity (UNFM)
Programmer Unfamiliarity (UNFM)
Only applies to modified software

---
Cost Factors
Cost Factors
Significant factors of development cost:
  - scale drivers are sources of exponential effort variation
  - cost drivers are sources of linear effort variation
    - product, platform, personnel and project attributes
    - effort multipliers associated with cost driver ratings
  - Defined to be as objective as possible
- Each factor is rated between very low and very high per rating guidelines
  - relevant effort multipliers adjust the cost up or down
[Speaker Notes: May be difficult to quantify, but better than ignoring important project factors (e.g. b asic vs. intermediate accuracies)]

---
Scale Factors
Scale Factors
Precedentedness (PREC)
  - Degree to which system is new and past experience applies
- Development Flexibility (FLEX)
  - Need to conform with specified requirements
- Architecture/Risk Resolution (RESL)
  - Degree of design thoroughness and risk elimination
- Team Cohesion (TEAM)
  - Need to synchronize stakeholders and minimize conflict
- Process Maturity (PMAT)
  - SEI CMM process maturity rating

---
Scale Factor Rating
Scale Factor Rating

---
Cost Drivers
Cost Drivers
Personnel factors
  - Analyst capability (ACAP)
  - Program capability (PCAP)
  - Applications experience (APEX)
  - Platform experience (PLEX)
  - Language and tool experience (LTEX)
  - Personnel continuity (PCON)
- Project Factors
  - Software tools (TOOL)
  - Multisite development (SITE)
  - Required schedule (SCED)
Product Factors
  - Reliability (RELY)
  - Data (DATA)
  - Complexity (CPLX)
  - Reusability (RUSE)
  - Documentation (DOCU)
- Platform Factors
  - Time constraint (TIME)
  - Storage constraint (STOR)
  - Platform volatility (PVOL)

---
Product Factors
Product Factors
Required Software Reliability (RELY)
  - Measures the extent to which the software must perform its intended function over a period of time.
  - Ask: what is the effect of a software failure

---
Example Effort Multiplier Values for RELY
Example Effort Multiplier Values for RELY
Very Low
Low
High
Very High
Slight Inconvenience
Low, Easily Recoverable Losses
High Financial Loss
Risk to Human Life
1.15
0.75
0.88
1.39
1.0
Moderate, Easily Recoverable Losses
Nominal

---
Example Effort Multiplier Values for RELY
Example Effort Multiplier Values for RELY
E.g. a highly reliable system costs 39% more than a nominally reliable system 1.39/1.0=1.39)
or a highly reliable system costs 85% more than a very low reliability system (1.39/.75=1.85)

---
Table 2.50 COCOMO II Scale Factors & Multipliers
Table 2.50 COCOMO II Scale Factors & Multipliers

---
Example Table-Based Estimation
Example Table-Based Estimation
Effort (person-months) = 2.94 (Size)E Π Σmi
E is an exponent for the diseconomy of scale dependent on five additive scale drivers according to b = .91 + .01 × Σ SFi,
where SFi is a weighting factor for ith scale driver
Example estimate: Size=30 KSLOC; RELY, CPLX = High; TOOL= High; All other scale factors and cost drivers = Nominal
E = 0.91 + .01 (3.72+3.04+4.24+3.29+4.68) = 0.91 + .1897 = 1.0997 ~ 1.1
Σmi = (1.10) × (1.17) × (0.90) = 1.1583
Size = 30 KSLOC
Effort = 2.94 × 30 1.1 × 1.1583 = 143.55 person-months

---
End of Unit 02 : Project Management, Planning and Risk Analysis